## Progress tracker
Project Start Date (v.20220927) | 2022-09-27 | ***MAKE A COPY OF THIS FILE BEFORE EDITING***
Project Owner OfficeRnD
Project Owner {Customer.Name}
Phase | Assigned to | Information needed | Progress/Status | Task priority for the overall implementation | Start date: Customer task (YYYY-MM-DD) | Deadline: Customer task (YYYY/MM/DD) | Start date: OfficeRnD task (YYYY-MM-DD) | Deadline: OfficeRnD task (YYYY/MM/DD) | Client approver | Completed (YYYY-MM-DD)
Preliminary Phase |  | Premium Mobile App (if applicable) Final Floorplan Request | Not started | Low
Preliminary Phase |  | Document Customizations (Contracts, Invoice, and/or Email Templates) [If included in deal and required] | Not started | Med
Phase 1 Business model & Pricing |  | The needed information is listed in every subphase below | Not started | High
Phase 1.1. Bookable resources |  | Pricing model & Revenue account Booking extras Availability (bookable by day/hour) Privacy (admin vs public vs active members) Booking flow & Cancellation policy Amenities (free of charge, e.g. WiFi, White board, etc.) Room image Results review & demo | Not started | High
FALSE |  | 1.1a - Pricing model & Revenue account |  | High
FALSE |  | 1.1b - Booking extras |  | Med
FALSE |  | 1.1c - Availability (bookable by day/hour) |  | High
FALSE |  | 1.1d - Privacy (admin vs public vs active members) |  | Med
FALSE |  | 1.1e - Booking flow & Cancellation policy |  | Med
FALSE |  | 1.1f - Amenities (free of charge, e.g. WiFi, White board, etc.) |  | Low
FALSE |  | 1.1g - Room image |  | Low
FALSE |  | 1.1h - Results review & demo (optional: include specific training module) |  | High
Phase 1.2. Monthly & One-off services |  | Pricing model & Revenue account Plan description Invoicing period (e.g. services sold on an annual basis) Privacy (Member apps’ settings) Discounts Credits/Coins for other services (e.g. meeting rooms or printing) Contracts vs Month-to-month memberships Optional: Plan image (if you’d like to make the service publicly visible) Optional: Turn off plan proration Optional: Setup fees or any additional charges paid once for this plan Optional: Plan Terms Results review & demo | Not started | High
FALSE |  | 1.2a - Pricing model & Revenue account |  | High
FALSE |  | 1.2b - Plan descriptions |  | Med
FALSE |  | 1.2c - Invoicing period (e.g. services sold on an annual basis) |  | Med
FALSE |  | 1.2d - Contracts vs Month-to-month memberships |  | High
FALSE |  | 1.2di - Contract types Review |  | High
FALSE |  | 1.2dii - Contract settings Review |  | High
FALSE |  | 1.2diii - ESign |  | High
FALSE |  | 1.2e - Privacy (Member apps’ settings) |  | Med
FALSE |  | 1.2f - Discounts |  | High
FALSE |  | 1.2g - Credits/Coins for other services (e.g. meeting rooms or printing) |  | High
FALSE |  | 1.2h - Optional: Plan image (if you’d like to make the service publicly visible) |  | Low
FALSE |  | 1.2i - Optional: Turn off plan proration |  | Low
FALSE |  | 1.2j - Optional: Setup fees or any additional charges paid once for this plan |  | Low
FALSE |  | 1.2k - Optional: Plan Terms |  | Low
FALSE |  | 1.2l - Results review & demo |  | High
Phase 2 Resources import |  | Import template (name, location, size, price, floor, deposit, type, area) Customer to check the imported information | Not started | High
FALSE |  | Desks | Not started | High
FALSE |  | Offices | Not started | High
Phase 3 Client data import |  | Companies Members Memberships (+ assigned resource) Customer to check the imported information | Not started | High
FALSE |  | 3.1 - Company Import |  | High
FALSE |  | 3.2 - Member Import |  | High
FALSE |  | 3.3 - Memberships Import |  | High
FALSE |  | 3.4 - Deposits (One-Off Fee Import) [optional] |  | Med
FALSE |  | 3.5 - Results Review / Audit |  | High
Phase 4 Main native integrations |  | Accounting Payment Gateway Printing Authentication Wi-Fi Door Access CRM Others | Not started | Med
FALSE |  | Accounting |  | Med
FALSE |  | Payment Gateway |  | Med
FALSE |  | Printing |  | Med
FALSE |  | Authentication |  | Med
FALSE |  | Wi-Fi |  | Med
FALSE |  | Door Access |  | Med
FALSE |  | CRM |  | Med
FALSE |  | Other Integrations |  | Low
Phase 5 Billing/Invoicing settings |  | Currency Billing period Start Date Proration Tax Application and Tax Rate Automated Bill Run (Generation, Issue/Due Date) Email notifications Purchase flows |  | High
FALSE |  | Currency |  | High
FALSE |  | Billing period Start Date |  | High
FALSE |  | Proration |  | High
FALSE |  | Tax Application and Tax Rate |  | High
FALSE |  | Automated Bill Run (Generation, Issue/Due Date) |  | High
FALSE |  | Email notifications |  | High
FALSE |  | Purchase flows |  | High
FALSE |  | Invoice number generation (for customers that use Xero or QB Online) |  | Med
Phase 6 Member facing tools |  | Member portal (sign-up pages, calendars) Rooms app Reception app T&C Templates (emails & documents like invoices + contracts) | Not started | Med
FALSE |  | 6.1a - Determine which member tools will be used |  | High
FALSE |  | 6.1b - Custom Domain for Member Portal (optional) |  | High
FALSE |  | 6.1c - Review the different sign-up and public calendar pages that we provide under Settings/Apps/Public Pages. |  | High
FALSE |  | 6.1e - Customize the pages of the Member Portal and their display order |  | High
FALSE |  | 6.1f - Design the overall theme (colors, images) for the Member Portal |  | High
Phase 7 Final review |  | Call with the stakeholders where OfficeRnD will present the final product and get confirmation that everything has been set up accordingly. | Not started | High
Phase 8 Admin team training |  | Help us organize training sessions with the team members that will use OfficeRnD on a daily basis where we will demo the tool for them | Not started | High
FALSE |  | Community (~1.5 hours) |  | High
FALSE |  | Meeting Room and Bookings (~45 minutes) |  | High
FALSE |  | Billing (~1 hour) |  | High
FALSE |  | Space and Inventory (~ 45 minutes) |  | High
Note on A10: Bookable resources (meeting rooms, event spaces, conference rooms, hot/flex desks, etc.)
Note on A19: Assignable resources (private offices, dedicated desks, parking slots, etc.)
Note on B6: Enter name of client responsible for providing the information needed by OfficeRnD
Note on E6: Priority of the item as it pertains to the overall implementation of that specific item.
Note on G6: Deadline agreed upon to have respective section completed by client for any requested data
Note on J6: Name of the client that would have to give their final approval for the completion of the phase (once OfficeRnD presents the implemented functionality/data)
Note on K6: Completed time by ORND for respective task